## Query Resolution Log
Date | Issue Description | Issue Area | Fix Done | Team Responsible
29/8/2024 | LEAP was not receiving all Appointments in realtime pipeline | LEAP Realtime service | Issue was investigated , but was not able to find a root cause. | Application Improvements
30/8/2024 | LEAP was not receiving Social Histories in realtime pipeline | LEAP Realtime service | Issue was investigated , but was not able to find a root cause. | Application Improvements
2024-02-09 | LEAP was unable to get patient bundles through bundle service | LEAP Bundle Sevice/ Kafka | Issue was with kafka. | SCM
2024-04-09 | LEAP was unable to get patient bundles through bundle service | LEAP Bundle Sevice/ Kafka | Issue was with kafka. | SCM
5/9/2024-6/9/2024 | LEAP was not receiving events in CDC pipeline | LEAP Realtime service | Not an issue , the events are delayed somewhere along the data pipeline . The delay never occurs on FHIR or Datalake end . These two areas have been timed multiple times to post data with in 1-2 mins . | SCM/LEAP
2024-10-09 | LEAP was not receiving events in CDC pipeline | LEAP Realtime service | Not an issue , the events are delayed somewhere along the data pipeline . The delay never occurs on FHIR or Datalake end . These two areas have been timed multiple times to post data with in 1-2 mins . | SCM/LEAP
2024-12-09 | LEAP team did not receive delete events in realtime pipeline | LEAP Realtime service | Not an issue , the events are delayed somewhere along the data pipeline . The delay never occurs on FHIR or Datalake end . These two areas have been timed multiple times to post data with in 1-2 mins . | SCM/LEAP
13/9/2024 | LEAP was not receiving Service Request in CDC pipeline | LEAP Realtime service | Not an issue , the events are delayed somewhere along the data pipeline . The delay never occurs on FHIR or Datalake end . These two areas have been timed multiple times to post data with in 1-2 mins . | SCM/LEAP
16/9/2024 | LEAP was not receiving Social History in CDC pipeline | LEAP Realtime service | Not an issue , the events are delayed somewhere along the data pipeline . The delay never occurs on FHIR or Datalake end . These two areas have been timed multiple times to post data with in 1-2 mins . | SCM/LEAP
20/9/2024 | LEAP was not receiving Diagnostic Report in CDC pipeline | LEAP Realtime service | Not an issue , the events are delayed somewhere along the data pipeline . The delay never occurs on FHIR or Datalake end . These two areas have been timed multiple times to post data with in 1-2 mins . | SCM/LEAP
20/9/2024-21/9/2024 | LEAP Bundle Sevice unable to connect to Kafka. Issue occurred due to minimum support of AWS msk for .NET | LEAP Bundle Service / App03 ports/ Kafka | Custom Authentication solution done by extending Kafka client functionalities | Application Improvements
23/09/2024 | PrimaryPerformer field not found in Appointment resource in a bundle . Code was missing that fetched practitioner appointment releation. | LEAP Bundle Sevice | Missing Checks Applied in service code. | Application Improvements
| LEAP was not receiving Diagnostic Report in CDC pipeline | LEAP Realtime service | Not an issue , the events are delayed somewhere along the data pipeline . The delay never occurs on FHIR or Datalake end . These two areas have been timed multiple times to post data with in 1-2 mins . | SCM/LEAP
| LEAP Bundle Service did not post a patient's bundle . It was not posted because the patient was a test patient | LEAP team / LEAP bundle service | LEAP team was told about the test patient checks in the bundle service , so that they avoid creating test patients in the future. | Application Improvements /LEAP
24/09/2024 | LEAP team reported that they were not receiving Lab Observation and Diagnostic Reports in there 10g order of formation. | LEAP Realtime service | Not an issue. A delay in the formation of Diagnostic Report was added in DataLake to avoid failure of resource due to failed references. This is a limitation of FHIR implementation | Application Improvements /LEAP
24/09/2024 | LEAP team reported that they were not receiveing diagnostic reports . | LEAP Realtime service | Not an issue , the events are delayed somewhere along the data pipeline . The delay never occurs on FHIR or Datalake end . These two areas have been timed multiple times to post data with in 1-2 mins . | SCM/LEAP
25/09/2024 | Realtime service stopped posting data to kafka due to missing Care Team resource topic in Kafka . CareTeam topic was not created by SCM at the related kafka instance | SCM | CareTeam topic was created by SCM. | SCM
25/09/2024-26/09/2024 | Bundle Service unable to post data on AWS S3 storage because authentication parameters provided to Application Improvements did not have rights to post data on a changed AWS S3 path. | AWS S3 /DataLake/SCM | Rights to post on the new S3 path were provided by SCM . | SCM
| LEAP Bundle Service did not post a patient's bundle . It was not posted because the patient was a test patient . LEAP team requested now that Bundle Service should give customised errors to notify the possible issues with data and events in the implementation. | LEAP team / LEAP bundle service | LEAP team was told about the test patient checks in the bundle service in the past . They were told about that again . Customised Error Handling has been done and deployed by Application Improvements on 27/09/2024 | LEAP
| PrimaryPerformer field not found in Appointment resource in a bundle . Issue was earlier fixed for release on 23/09/2024 , but the latest package was not deployed on App03 | LEAP Bundle Sevice | Latest package deployed on App03 | Application Improvements
| LEAP bundle service was fetching all Provider Specialties for providers linked to Appointment. LEAP team requested a limit to be placed on the number of Provider Specialties. It is something that cannot be catered in FHIR , since there is almost no available filtering factor in 10g Database . It may require a change in 10g application. | 10G | Under Discussion . Data for number of provider specialties has been fetched for all providers of live practices . The issue did not proceed ahead of discussion. | 10g / Analysis/Application Improvements
26/09/2024-27/09/2024 | LEAP realtime service was sending unwanted and irrelevant delete event payloads to DataLake. Delete event implemention in LEAP realtime service was missing certain checks . | LEAP Realtime Service | The issue has been fixed and deployments have been made to App03. | Application Improvements
26/09/2024-present | Surgical History , Social History , Medical History and Family Member History triggers and services do not have delete functionality . An earlier agreed upon requirement was now conflicted by LEAP team personnel. | LEAP Realtime Service/ LEAP Bundle Service /Database | The relevant changes have been implemented and deployed on all environments as of 23/ 10/2024 , though a last minute change in requirements from LEAP side has resulted in incomplete resolution still . LEAP wants application improvements to custom develop Delete functionality for just 3 resources . The issue can be easily resolved by extensions (as suggested by Application Improvements). The suggestions are under review by LEAP team. | LEAP team / Application Improvements / 10g
1/10/2024-10/10/2024 | LEAP realtime/CDC pipleine was creating payloads with missing TenantIDs for pharamacy based resources | 10G | After investigation ,it was found that issue actually occurred because of 10g implementation of pharmacies . The issue has been ignored for the time being , because LEAP is not using Pharmacy based resources in current MVP , though they were all developed for them (effort on development is wasted unless they use it in some form in future ). | 10g (EHR Prescriptions)
2024-03-10 | Kafka events produced by LEAP were not being received by LEAP patient bundle service on App03 | Kafka | The issue was not reproducible again and after sometime service began receiving and processing events (without any change) . | SCM
2024-07-10 | LEAP team was not receiveing patient histories in CDC | LEAP Realtime Service | Patient Histories was switched off mistakenly by Application Improvements through configuration.Issue was resolved the same day. | Application Improvements
2024-08-10 | Kafka events produced by LEAP were not being received by LEAP patient bundle service on App03 | Kafka | No possible reason was found for the issue , but it was resolved by re-deployment on App03. | Application Improvements
11/10/2024-14/10/2024 | LEAP team was not receiving CDC payloads for Medication Request on App03 | LEAP Realtime Service | Medication Request query was failing as a ripple of a change done to fetch Refill Request status . The error was indirect result of urgent development of requested changes . If given enough time , the change would have been first tested and developed at all ends on release. | Application Improvements /LEAP
14/10/2024 | LEAP team asked if LEAP Realtime service was running | LEAP Realtime service | Not an issue , the events are delayed somewhere along the data pipeline . The delay never occurs on FHIR or Datalake end . These two areas have been timed multiple times to post data with in 1-2 mins . | SCM/LEAP
16/10/2024 | LEAP team and QA Integration reported that they were not receiving diagnostic Report resource in CDC pipeline | LEAP Realtime Service | Not an issue . Logs for LEAP Realtime service showed successful posting of payloads for the given IDs. | LEAP / QA Integration
16/10/2024 - 17/10/2024 | LEAP team was not receiving any CDC payloads | 10g | Issue occurred due to DB error . | 10g / Databases /SCM
16/10/2024 -24/10/2024 | LEAP team was not receiving localized (UTC) time fields in LEAP -FHIR services | 10g / LEAP Realtime service / LEAP Bundle Service | The switch to UTC time fields was evaluated around March 2024 , however the change was not done due to inaedequate utilization by 10g application of UTC datetime fields . The change was reevaluated and for certain DB tables it was found that utilization was below 90 % for upto 400 live clients . Application Improvements developed and deployed the necessary changes in services on 24/10/2024 Application Improvements along with PMO and Analysis is managing the resolution of data discrepancies w.r.t 10g teams. | 10G / Application Improvements
24/10/2024 | LEAP team asked to check (after office hours) if LEAP realtime service was up and running on release server . | Kafka | Relevant Kafka instance was down , asked Devops to resolve the issue . | SCM

## Modification Requests
Date | Description | Update done | Comments
20/8/2024-23/8/2024 | LEAP team requested urgent addition of ShowOnPortal bits as extensions in Encounter and Diagnostic Report | Change done as requested
26/8/2024 | LEAP team requested sending of Codeable Concept element in LEAP -FHIR services for Medication Request element. | Change done as requested
29/8/2024 | LEAP team and Devops asked for creation of a separate data source for a second LEAP instance (demo). | Change done as requested | Baseline01/Leap_CureMD was created and configured with LEAP services . However the environment was not used afterwards.
2/9/2024-6/9/2024 | LEAP team requested for addition of medication codeable concept in Medication Request FHIR resource. | Change done as requested
2024-12-09 | LEAP team asked for addition of Patient Instruction (which already existed in resource) and Laboratory name as extensions in both Diagnostic reports and Service Request . | Change done as requested
20/9/2024-21/9/2024 | LEAP Bundle Sevice unable to connect to Kafka. Issue occurred due to minimum support of AWS msk for .NET | Custom Authentication solution done by extending Kafka client functionalities | The solution was also shared with Datalake and LEAP team for implementation on there side
23/09/2024 | LEAP team requested addition of shortname as extension in Orders and Results based resources | Change done as requested
25/09/2024-26/09/2024 | LEAP bundle service was fetching all Provider Specialties for providers linked to Appointment. LEAP team requested a limit to be placed on the number of Provider Specialties. It is something that cannot be catered in FHIR , since there is almost no available filtering factor in 10g Database . It may require a change in 10g application. | No update done
30/9/2024-24/10/2024 | LEAP team requested development of deletion process for histories and condition resources | Trigger update developed and tested in cooperation with Furqan 10/3/2024 . Service level changes done too and deployed on 24/10/2024 | Change pending on DataLake end due to last minute change of requirements from LEAP side
2024-02-10 | Datalake on behalf of LEAP team asked Application Improvements to redirect App03 Demo DB payloads to Release01 relevant Kafka instance (Production environment payloads to testing environment kafka ). | Change done as requested | This change was later reverted (App03 was routed again to Production ). The effort on the change was wasted as such.Extra effort was also wasted due to miscommunication by LEAP team (They earlier said that change was only needed for bundle service.)
2024-02-10 | LEAP team asked addition of acknowledgement status in Result based resources and Refill Request status in Medication Request | Change done as requested
9/10/2024-21/10/2024 | Deletion of Orders was not occuring in FHIR pipeline. Triggers needed update to cater hard deletion in the FHIR pipeline for soft deleted 10g records . | Change done as needed | Research on the handling was done and Trigger update was developed and tested in cooperation with Furqan .
2024-11-10 | Datalake asked Application Improvements to develop a payload element that will only be populated in LEAP CDC payloads to make identification between FHIR and LEAP payloads when both realtime services are routed to same kafka instance on Production environments. | Change in progress
11/10/2024-14/10/2024 | Datalake / LEAP teams asked us to change kafka instance for Release01 to 18.216.250.107:9092 | Change done as requested
14/10/2024 | LEAP team asked Application Improvements again to change kafka instance configuration on App03 to Production instance | Change done as requested | The change done on 2/10/2024 was reverted .Application Improvements made sure that this was a documented change .
15/10/2024 | LEAP team asked for deletion events for Medication Request | No update done | Not possible to implement delete triggers because of the way the 10g DB implementation of Medication Request. In response a new extension for medication ID was delivered to ease the handling on LEAP side .
16/10/2024 -24/10/2024 | LEAP team asked to shift Datetime element sourcs to localized (UTC)datetime fields in LEAP -FHIR services | Change done as requested | The switch to UTC time fields was evaluated around March 2024 , however the change was not done due to inaedequate utilization by 10g application of UTC datetime fields . The change was reevaluated and for certain DB tables it was found that utilization was below 90 % for upto 400 live clients . Application Improvements developed and deployed the necessary changes in services on 24/10/2024 Application Improvements along with PMO and Analysis is managing the resolution of data discrepancies w.r.t 10g teams.
18/10/2024 - present | LEAP team asked all Practitioners be sent along with the first patient bundle of the practice | Change in progress | Will be delivered on 1/11/2024